https://jira.tcsbank.ru/browse/INCR-627

##### План работ

| № | Начало | Длительность | Ответственный | Операция | Результат/Примечание |
| --- | --- | --- | --- | --- | --- |
| 1 | 22:00 | 1 минута | unix-admins | Отписаться в канал #unix-dba о начале работ |  |
| 2 | 22:01 | 10 минут | unix-admins | Выставить downtime в nagios и собрать sosreport |  |
| 3 | 22:11 | 30 минут | oradba | Остановить все экземпляры Oracle, которые работают на сервере m1-db23-stb |  |
| 4 | 22:41 | 30 минут | unix-admins | Выполнить контрольную перезагрузку сервера | Чтобы убедиться, что на сервере нет проблем |
| 5 | 23:11 | 9 минут | unix-admins | Создать бэкап /boot и снапшоты LVM |  |
| 6 | 23:20 | 60 минут | unix-admins | Выполнить обновление ОС до RHEL 7.7(3.10.0-1062.18.1.el7.x86_64) согласно инструкции |  |
| 7 | 00:20 | 90 минут | dct-team | Обновить Firmware(spp+bios) до последней версии. |  |
| 8 | 01:50 | 60 минут | oradba | Выполнить перелинковку исполняемых файлов и библиотек для всех экземпляров Oracle |  |
| 9 | 02:50 | 30 минут | oradba | Запустить экземпляры Oracle |  |
| 10 | 03:20 | 10 минут | unix-admins | Проверить логи ОС на наличие ошибок |  |
| 11 | 03:30 | 1 минута | unix-admins | Снять downtime в nagios |  |
| 12 | 03:11 | 1 минута | unix-admins | Отписаться в канал #unix-dba об окончании работ |  |

В случае возникновения проблем, которые не позволяют выполнить работы, перейти к плану отката

##### План отката

| № | Длительность | Ответственный | Операция | Результат/Примечание |
| --- | --- | --- | --- | --- |
| 1 | 20 минут | unix-admins | Откатить снапшоты LVM и перезагрузить сервер m1-db23-stb |  |
| 2 | 60 минут | oradba | Выполнить перелинковку исполняемых файлов и библиотек для всех экземпляров Oracle |  |
| 3 | 30 минут | oradba | Запустить экземпляры Oracle |  |
| 4 | 10 минут | unix-admins | Проверить логи ОС на наличие ошибок |  |
| 5 | 1 минута | unix-admins | Отписаться в канал #unix-dba об окончании работ |  |

[15:54:47 root@m1-db23-stb ~]# findmnt -t nfs -o TARGET | grep -ie "oramnt" | sed -e 's/^\/oramnt\///'

BPM_prod_arch

FILENET_prod_arch

listener_prod

ESB_MSGS

CREDB

ESB

INFORM_prod_arch

ESB_prod_arch

SIEBEL_prod_arch

FILENET

XXI_prod_arch

TI_GW_prod_arch

SASAUX

SSO

TI_GW

DFINANS

SSO_prod_arch

DFINANS_prod_arch

INFORM

SIEBEL

BB_DTA

ILOG_BPM

EDA

ESB_MSGS_prod_arch

XXI_MFO_prod_arch

ILOG_BPM_prod_arch

XXI

SASAUX_prod_arch

BB_DTA_prod_arch

BPM

EDA_prod_arch

XXI_MFO

CREDB_prod_arch

AML_prod_arch

AML

AVAYA_prod_arch

AVAYA

BSS17_prod_arch

BSS17

BUFF_prod_arch

BUFF

CRYPTO_prod_arch

CRYPTO

EMREP_prod_arch

EMREP

EVAM_prod_arch

EVAM

HRSPACE_prod_arch

HRSPACE

LOYALTY_prod_arch

LOYALTY

REPORTS_prod_arch

REPORTS

RMCAT

RMCAT_prod_arch

SD_prod_arch

SD

SPAREPRM_prod_arch

SPAREPRM

WFM_prod_arch

WFM

WOF_prod_arch

WOF

TRADE_prod_arch

RSTINK_prod_arch

RSTINK

XLTINK_prod_arch

XLTINK

TRADE

SME_prod_arch

PRM_prod_arch

PRM

RSC

RSC_prod_arch

SME

rmanbackups

ohbackups

ACC

ACC_prod_arch

[15:55:08 root@m1-db23-stb ~]#

#

#	All licences were used.

#

[16:05:53 root@m1-db23-stb ~]# subscription-manager status

+-------------------------------------------+

System Status Details

+-------------------------------------------+

Overall Status: Unknown

[16:06:39 root@m1-db23-stb ~]# subscription-manager list

+-------------------------------------------+

Installed Product Status

+-------------------------------------------+

Product Name:   Red Hat Enterprise Linux Server

Product ID:     69

Version:        7.5

Arch:           x86_64

Status:         Unknown

Status Details:

Starts:

Ends:

[16:07:12 root@m1-db23-stb ~]# egrep -e "^proxy_hostname|^proxy_port|^proxy_user|^proxy_password" /etc/rhsm/rhsm.conf

proxy_hostname =proxy.tcsbank.ru

proxy_port =8080

proxy_user =rhsm_user

proxy_password =6eKoEvNHFS5IycxhqH5W

[16:07:28 root@m1-db23-stb ~]# read -s -p "Enter RHN Password: " RHN_PASSWORD ; subscription-manager register --username=tcsbank17012012 --password=$RHN_PASSWORD --auto-attach

Enter RHN Password: Registering to: subscription.rhsm.redhat.com:443/subscription

The system has been registered with ID: fd612839-f321-4d83-b7ca-45cb6f094dde

The registered system name is: m1-db23-stb

Installed Product Current Status:

Product Name: Red Hat Enterprise Linux Server

Status:       Not Subscribed

Unable to find available subscriptions for all your installed products.

[16:08:44 root@m1-db23-stb ~]# subscription-manager status

+-------------------------------------------+

System Status Details

+-------------------------------------------+

Overall Status: Invalid

Red Hat Enterprise Linux Server:

- Not supported by a valid subscription.

[16:10:02 root@m1-db23-stb ~]# read -s -p "Enter RHN Password: " RHN_PASSWORD ; subscription-manager register --username=tcsbank17012012 --password=$RHN_PASSWORD --auto-attach

Enter RHN Password: This system is already registered. Use --force to override

[16:11:11 root@m1-db23-stb ~]# subscription-manager status

+-------------------------------------------+

System Status Details

+-------------------------------------------+

Overall Status: Invalid

Red Hat Enterprise Linux Server:

- Not supported by a valid subscription.

[16:11:59 root@m1-db23-stb ~]# read -s -p "Enter RHN Password: " RHN_PASSWORD ; subscription-manager register --username=tcsbank17012012 --password=$RHN_PASSWORD --auto-attach --force

Enter RHN Password: Unregistering from: subscription.rhsm.redhat.com:443/subscription

The system with UUID fd612839-f321-4d83-b7ca-45cb6f094dde has been unregistered

All local data removed

Registering to: subscription.rhsm.redhat.com:443/subscription

The system has been registered with ID: 85c632f5-dc8e-4259-b597-6c9d3a1ded0a

The registered system name is: m1-db23-stb

Installed Product Current Status:

Product Name: Red Hat Enterprise Linux Server

Status:       Not Subscribed

Unable to find available subscriptions for all your installed products.

[16:12:56 root@m1-db23-stb ~]#

https://access.redhat.com/management/systems/cd35fb5a-2317-4503-b14b-3e97b3d88c18/subscriptions

................................................................................

[s.belogrud@TCS4357]# ssh bsv@m1-db24-stb

Last login: Thu Mar  5 21:13:09 2020 from tcs4357.tcsbank.ru

[bsv@m1-db24-stb ~]$ sudo -i

[sudo] password for bsv:

Sorry, try again.

[sudo] password for bsv:

[16:19:46 root@m1-db24-stb ~]# subscription-manager status

+-------------------------------------------+

System Status Details

+-------------------------------------------+

Overall Status: Current

System Purpose Status: Not Specified

[16:20:03 root@m1-db24-stb ~]# subscription-manager remove --all && subscription-manager unregister

1 local certificate has been deleted.

1 subscription removed at the server.

Unregistering from: subscription.rhsm.redhat.com:443/subscription

System has been unregistered.

[16:22:48 root@m1-db24-stb ~]# subscription-manager status

+-------------------------------------------+

System Status Details

+-------------------------------------------+

Overall Status: Unknown

System Purpose Status: Unknown

[16:23:59 root@m1-db24-stb ~]#

................................................................................

[16:22:57 root@m1-db23-stb ~]# read -s -p "Enter RHN Password: " RHN_PASSWORD ; subscription-manager register --username=tcsbank17012012 --password=$RHN_PASSWORD --auto-attach --force

Enter RHN Password: Unregistering from: subscription.rhsm.redhat.com:443/subscription

The system with UUID 85c632f5-dc8e-4259-b597-6c9d3a1ded0a has been unregistered

All local data removed

Registering to: subscription.rhsm.redhat.com:443/subscription

The system has been registered with ID: 4b7c54f1-4651-415e-be5c-5a38d3ccc6e4

The registered system name is: m1-db23-stb

Installed Product Current Status:

Product Name: Red Hat Enterprise Linux Server

Status:       Subscribed

[16:23:44 root@m1-db23-stb ~]#

................................................................................

#

#	And now the server m1-db24-stb is absent here

#

https://access.redhat.com/management/systems

[16:26:58 root@m1-db23-stb ~]# subscription-manager list

+-------------------------------------------+

Installed Product Status

+-------------------------------------------+

Product Name:   Red Hat Enterprise Linux Server

Product ID:     69

Version:        7.5

Arch:           x86_64

Status:         Subscribed

Status Details:

Starts:         07/14/2020

Ends:           07/14/2021

[16:33:59 root@m1-db23-stb ~]#

[16:33:59 root@m1-db23-stb ~]# subscription-manager release --list

+-------------------------------------------+

Available Releases

+-------------------------------------------+

7.0

7.1

7.2

7.3

7.4

7.5

7.6

7.7

7.8

7.9

7Server

[16:34:55 root@m1-db23-stb ~]#

[16:34:55 root@m1-db23-stb ~]# yum list kernel --show-duplicates --disablerepo="*" --enablerepo="rhel-7-server-rpms" | head

Loaded plugins: langpacks, product-id, search-disabled-repos, subscription-

: manager

Repodata is over 2 weeks old. Install yum-cron? Or run: yum makecache fast

Installed Packages

kernel.x86_64              3.10.0-693.17.1.el7               @anaconda/7.4

kernel.x86_64              3.10.0-862.14.4.el7               @rhel-7-server-rpms

Available Packages

kernel.x86_64              3.10.0-123.el7                    rhel-7-server-rpms

kernel.x86_64              3.10.0-123.1.2.el7                rhel-7-server-rpms

kernel.x86_64              3.10.0-123.4.2.el7                rhel-7-server-rpms

kernel.x86_64              3.10.0-123.4.4.el7                rhel-7-server-rpms

[16:35:34 root@m1-db23-stb ~]#

[17:56:58 root@m1-db23-stb ~]# export rootvg=$(lvs --noheadings -o vg_name -S lv_dm_path=`findmnt -r -n -o SOURCE /`| tr -d ' ')

[17:57:05 root@m1-db23-stb ~]# vgs -S vg_name=$rootvg

VG     #PV #LV #SN Attr   VSize VFree

rootvg   1   5   0 wz--n- 1.09t 442.56g

[17:57:42 root@m1-db23-stb ~]#

По причине проведения ночных работ “Обновление m1-db23-stb” (https://jira.tcsbank.ru/browse/INCR-627) с 22:00 21.01.2021 по 3:00 22.01.2021 планирую подключиться в пятницу к работе позже на ~5 часов.